## work list
Work parcel | Parish | FP number | location | Grid ref(SO) | work | when(mm/yy) | comment
1 | CM | 54 | eaglelane | 673755 | repair rotten stile upright | 3/16 | Needs geoff to inspect and identify work needed
1 | CM | 54 | eaglelane | 673755 | renovate flight of wooden steps | 3/16
2 | Neen Savage | 30 | ghost house | 667765 | Replace stile with KG | 4/16 | also open up permissive route
3 | CM | 52 | Barnsland | 664744 | replace stile step | 5/16 | may possibly remove stile.
3 | CM | 53 | Barnsland | 667743 | resite step | 5/16 | Do clearance at the same time
3 | CM | 53 | Barnsland | 665736 | make step firmer | 5/16
4 | Neen Savage | 7 | musbatch | 673772 | replace rotten stile with gate | 6/16 | also some clearance in same area
5 | Neen Savage | 28Y | wyre Farm | 687772 | KG on permissive line |  | need SC to get permission
5 | Neen Savage | 28 | wyre Farm | 684772 | Replace stile with KG |  | permission from Pioneer Centre
5 | Neen Savage | 28Y | wyre Farm | 684771 | Replace stile with KG |  | need SC to get permission
6 | Neen Savage | 22 | little stepple | 655773 to 659775 | 5 waymark posts | 9/16 | this path has been diverted so waymarking essential
7 | Milson | 3 | Langley | 650733 | Footbridge |  | need joint WP with SC
7 | Milson | 3 | Langley | 650733 | new stile |  | also waymark FP3 & 2
8 | CM | 50 | dudnill | 643744 | replace stile with gate |  | low priority
9 | hopton wafers | 8(BW) | Catherton | 660794 | waymark post |  | long walk in for small job

## wish list
Parish | FP number | location | Grid ref(SO) | Help needed from SC
Milson | 12 | village centre | 635733 to 639730 | Path needs opening up, SC to reach agreement with landowner on work
Neen Sollars | 25 | village centre | 662725 to 663723 | Path needs opening up, SC to reach agreement with landowner on work
Neen Savage | 68 | Baveney | 699797 | make landowner move fence as path far too narrow
Hopton Wafers | 16 | The Glebe |  | obstructed path/make landowner pay for diversion | NEW

## diversion issues
Parish | location | path number | issue | current situation | note
CM | Caravan park | 44 | definitive map error | in progress | DMMO was issued but objections. No action for sometime
Neen Savage | Overwood farm | 68Y | dead end path | in progress | no action for sometime
Neen Savage | Wyre common | 71 to 75 | Re-alignment of paths needed | in progress | consultation ongoing
CM | furnace mill | 8 | current line of path obstructed, needs to be diverted onto walkable line | unknown | Was with Kevin.
Hopton wafers | Little woodhouse | 59 | no footbridge on definitive line. Alternative not safe | no action. | agreed in principle. Needs to be started
Neen Sollars | River rea | 11 & 13 | 2 missing FB/combine to one | no action. | Needs cross border project
Kinlet | Dowles brook | 64 | riverside erosion. Needs diversion | no action. | landowner approached without success
Neen Savage | Stepple Hall | 14 | dead end path | no action. | needs landowner discussions to progress